## Combined
This project plan timeline provides estimates for how long components of a marketing campaign take. The tasks + timing below serve as examples; the duration in the blue rows indicates the number of business days it will take in total and all days below should add up to that number. Please delete and add sections and adjust times as needed. Some project management software, such as Microsoft Project, will update all dates automatically each time that you adjust one. Please see additional tabs below for additional ways to keep track of milestones and project plans.
CAMPAIGN NAME
Project Plan
Date
Task Name | Duration | Start | Finish | Responsibility
Vendor Procurement | 10 - 20 days |  |  | TEAM(S) OR INDIVIDUAL(S) RESPONSIBLE
If your campaign will involve vendor procurement (e.g. the use of an external marketing agency), include steps required here by inserting lines with the action items that need to be done and the anticipated duration + dates. If vendor procurement is not needed, delete this section. | NA
Onboarding/Discovery | 9 - 15 days
Campaign kick-off meeting to review timing, discuss ways of working, how communication will work, etc. | 1 day
Existing research, past campaign performance, etc. shared | 2-3 days
Synthesize and analyze existing data | 5-10 days
Share summary with team | 1 day
Audience Research | 31 - 65 days
Develop Audience Research Brief | 3-5 days
Share Audience Research Brief with team for input | 1 day
Finalize Research Brief | 2 days
Develop respondent recruiting copy + lead collection landing page | 3-5 days
Provide copy to X for deployment | 1 day
Recruit respondents | 5-15 days
Screen/schedule respondents | 5-10 days
Conduct ethnographic audience interviews | 5-15 days
Synthesize and analyze findings | 5 - 10 days
Present audience analysis, segments and personas | 1 day
Strategy Development | 22 days
Develop Value Proposition and Creative Brief | 5 days
Share Value Proposition and Creative Brief with team for input | 1 day
Finalize Value Proposition and Creative Brief | 2 days
Conduct competitive research | 5 days
Develop Marketing Communication Strategy | 5 days
Share Marketing Communication Strategy for input | 1 day
Finalize Marketing Communicaiton Strategy | 3 days
Creative Concepting | 9 - 16 days
Develop Creative Concepts (Scripts) | 5-10 days
Share Creative Concepts with team for input | 1 day
Finalize Creative concepts | 3-5 days
Creative Validation | 25 - 37 days
Develop Concept Validation Brief | 3 - 5 days
Share Brief with team for input | 1 day
Finalize Brief | 2 - 3 days
Develop Survey questions | 3-5 days
Share Survey questions for input | 1
Finalize Survey questions | 2-3 days
Set-up Survey test in SurveyMonkey | 3-5 days
Quality Assurance (QA) Survey Set-up | 2 days
Field test | 3 - 5 days
Share out initial findings/identy winner | 1 day
Develop analysis | 3 - 5 days
Share analysis with team | 1 day
Media Planning | 13 - 20 days
Develop Media Flowchart based on provided Marketing Communication Strategy | 5 - 10 days
Share with team for input | 1 day
Revise Media Flowchart | 3 - 5 days
Share with team for input | 1 day
Finalize Media Flowchart | 1 day
Provide team with all required creative asset specifications | 1 day
Update Creative Brief with required creative asset specifications | 1 day
Creative Production | 57 - 92 days
Using winning concept, develop treatments for different formats (video, banner, OOH, display, etc.) | 5 - 10 days
Share treatments with team for input | 1 day
Revise treatments | 3 - 5 days
Share with creative treatments with team for final input | 1 day
Finalize creative treatments | 2 - 3 days
Video pre-production (location scouting, talent, etc.) | 5 - 10 days
Video shoot | 1 - 3 days
Video editing | 5 days
Share :30 video rough cut with team for input | 2 - 3 days
Revise rough cut | 2 - 3 days
Share revised rough cut with team for input | 1 - 2 days
Finalize rough cut | 1 day
Produce :30 spot | 2 - 3 days
Develop :15 cut-down | 2 - 3 days
Share :15 cut-down with team for input | 1 - 2 days
Final approval cut-down | 1 day
Produce :15 spot | 1 day
Develop :15 cut-down and :12 social videos | 3 - 5 days
Share :15 cut-down and :12 social videos with team for input | 2 - 3 days
Finalize :15 and :12 videos | 2 - 3 days
Final approval video assets | 1 day
Develop OOH, display, and any other required assets | 5 - 10 days
Share OOH, display, etc assets with team for input | 2 - 3 days
Finalize OOH, display, etc assets | 3 - 5 days
Build/package creative assets for trafficking | 3 - 5 days
Tracking & Analysis | 22 - 35 days
Media tracking requirements provided | 3 - 5 days
Tracking implementation | 2 - 3 days
Q/A to validate placement of tracking and data transfer | 2 - 3 days
Dashboard requirements drafted | 2 - 3 days
Dashboard requirements to team for input | 2 - 3 days
Finalize Dashboard requirements | 1 day
Set-up of campaign dashboard | 5 - 7 days
Validation of data in campaign dashboard | 3 - 5 days
Dashboard goes live | 1 day
Validate live campaign data going into dashboard | 1 day
Media Execution | 10 - 16 days
Final negotiation with vendors | 3 - 5 days
Issue insertion orders | 3 - 5 days
Develop trafficking matrix | 2 - 3 days
Traffic creative units | 2 - 3 days
Launch | 6 days
Go live | 1 day
Daily updates provided to team | 5 days
Optimization | Ongoing
Daily monitoring of campaign performance | daily
Weekly campaign optimization calls | weekly

## Expedited Project Plan
Task Name | Number of Days | Start | Finish | Responsibility
Paid Search Launch | 22 | Fri 3/15/24 | Wed 4/17/24
Confirm website/pages paid search will drive traffic to | 0 | Fri 3/15/24 | Fri 3/15/24
Develop paid search strategy, recommended budget, keywords and copy | 5
Develop paid search tracking recommendation | 5
Share paid search strategy, recommended budget, keywords and copy with team for input | 0
Share paid search tracking recommendation with team for implementation | 3
Team to provide strategy/budget/keyword/copy feedback | 3
Implement and validate required campaign tracking | 5
Revise paid search strategy, budget, keywords and copy | 3
Finalize paid search strategy, budget, keywords and copy | 2
Build out paid search campaign | 3
Go live | 1
Begin weekly reporting | 5 |  |  |  | =
Task Name | Number of Days | Start | Finish | Responsibility
Paid Social Launch (assumes verified Facebook page exists) | 25 | Mon 3/25/24 | Mon 4/29/24
Develop Meta quick launch recommendation (budget and targeting strategy) | 10 | Mon 3/25/24 | Mon 4/8/24
Share Meta quick launch recommendation + creative specs with team for input | 3
Revise Meta quick launch recommendation | 3
Finalize Meta quick launch recommendation | 2
Develop static and dynamic creative assets | 5
Share static and dynamic creative assets with team for input | 2
Revise static and dynamic creative assets | 2
Finalize static and dynamic creative assets | 1
Build campaign | 1
Go live | 1
Begin weekly reporting | 5

## Milestones
COLLABORATING TEAM NAMES
MARKETING CAMPAIGN NAME
START DATE
Milestones | Number of Days | Start | Finish
Vendor Procurement | #REF! | #REF! | #REF!
Draft Mini-Bid and Vendor Selection Scorecard | 3 days | Fri 1/19/24 | Tue 1/23/24
Review Mini Bid and Scorecard with internal stakeholders | 1 day | Wed 1/24/24 | Wed 1/24/24
Mini-Bid and Venddor Selection Scorecard Approval | 1 day | Thu 1/25/24 | Thu 1/25/24
Establish Vendor Selection Committee and Mini-Bid Administrator | 0 days | Thu 1/25/24 | Thu 1/25/24
Issue Mini-Bid solicitation | 1 day | Fri 1/26/24 | Fri 1/26/24
Question submission period | 3 days | Mon 1/29/24 | Wed 1/31/24
Question responses issued | 2 days | Thu 2/1/24 | Fri 2/2/24
Receive Vendor proposals | 5 days | Mon 2/5/24 | Fri 2/9/24
Schedule Vendor meetings | 2 days | Mon 2/12/24 | Tue 2/13/24
Vendor presentations | 3 days | Wed 2/14/24 | Fri 2/16/24
Score and select vendor based on Scorecard results | 1 day | Tue 2/20/24 | Tue 2/20/24
Vendor Notification | 1 day | Wed 2/21/24 | Wed 2/21/24
Issue PO | 5 days | Thu 2/22/24 | Wed 2/28/24
Debrief sessions with Vendors (if requested) | 5 days | Thu 2/29/24 | Wed 3/6/24
Onboarding/Discovery | #REF!
Campaign kick-off meeting to review timing, discuss ways of working, how communication will work, etc. | 1 day | Wed 1/24/24 | Wed 1/24/24
Existing research, past campaign performance, etc. shared with OOI | 2 days | Thu 1/25/24 | Fri 1/26/24
Synthesize and analyze existing data | 5 days | Mon 1/29/24 | Fri 2/2/24
Share summary with team | 5 days | Mon 2/5/24 | Fri 2/9/24
Vendor Kick-Off meeting | 2 days | Thu 2/29/24 | Fri 3/1/24
Audience Research | 26
Share Audience Research Brief with team for input | 1 day | Wed 1/24/24 | Wed 1/24/24
Finalize Research Brief | 2 days | Thu 1/25/24 | Fri 1/26/24
Develop respondent recruiting copy + lead collection landing page | 0 days | Fri 1/26/24 | Fri 1/26/24
Provide recruiting copy to OSHE/HESAA for deployment | 0 days | Fri 1/26/24 | Fri 1/26/24
Recruit respondents | 10 days | Mon 1/29/24 | Fri 2/9/24
Screen/schedule respondents | 10 days | Tue 1/30/24 | Mon 2/12/24
Conduct ethnographic audience interviews | 10 days | Wed 1/31/24 | Tue 2/13/24
Synthesize and analyze findings | 10 days | Wed 2/14/24 | Wed 2/28/24
Present audience analysis, segments and personas | 1 day | Thu 2/29/24 | Thu 2/29/24
Strategy Development | 14
Develop Value Proposition and Creative Brief | 5 days | Fri 3/1/24 | Thu 3/7/24
Share Value Proposition and Creative Brief with team for input | 1 day | Fri 3/8/24 | Fri 3/8/24
Finalize Value Proposition and Creative Brief | 1 day | Mon 3/11/24 | Mon 3/11/24
Conduct competitive research | 7 days | Fri 3/1/24 | Mon 3/11/24
Develop Marketing Communication Strategy | 5 days | Tue 3/12/24 | Mon 3/18/24
Share Marketing Communication Strategy for input | 1 day | Tue 3/19/24 | Tue 3/19/24
Finalize Marketing Communicaiton Strategy | 1 day | Wed 3/20/24 | Wed 3/20/24
Creative Concepting | 10
Develop Creative Concepts (Scripts) | 5 days | Tue 3/12/24 | Mon 3/18/24
Share Creative Concepts with team for input | 2 days | Tue 3/19/24 | Wed 3/20/24
Finalize Creative concepts | 3 days | Thu 3/21/24 | Mon 3/25/24
Creative Validation | 24
Develop Concept Validation Brief | 2 days | Fri 3/8/24 | Mon 3/11/24
Share Brief with team for input | 2 days | Tue 3/12/24 | Wed 3/13/24
Finalize Brief | 1 day | Thu 3/14/24 | Thu 3/14/24
Develop Survey questions | 2 days | Fri 3/15/24 | Mon 3/18/24
Share Survey questions for input | 2 days | Tue 3/19/24 | Wed 3/20/24
Finalize Survey questions | 1 day | Thu 3/21/24 | Thu 3/21/24
Set-up Survey test in SurveyMonkey | 3 days | Fri 3/22/24 | Tue 3/26/24
QA Survey Set-up | 2 days | Wed 3/27/24 | Thu 3/28/24
Field test | 3 days | Mon 4/1/24 | Wed 4/3/24
Share out initial findings/identy winner | 1 day | Thu 4/4/24 | Thu 4/4/24
Develop analysis | 4 days | Fri 4/5/24 | Wed 4/10/24
Share analysis with team | 1 day | Thu 4/11/24 | Thu 4/11/24
Media Planning | 16
Develop Media Flowchart based on provided Marketing Communication Strategy | 5 days | Thu 3/21/24 | Wed 3/27/24
Share with team for input | 2 days | Thu 3/28/24 | Mon 4/1/24
Revise Media Flowchart | 3 days | Tue 4/2/24 | Thu 4/4/24
Share with team for input | 2 days | Fri 4/5/24 | Mon 4/8/24
Finalize Media Flowchart | 2 days | Tue 4/9/24 | Wed 4/10/24
Provide team with all required creative asset specifications | 1 day | Thu 4/11/24 | Thu 4/11/24
Update Creative Brief with required creative asset specifications | 1 day | Fri 4/12/24 | Fri 4/12/24
Creative Production | 72
Using winning concept, develop treatments for different formats (video, banner, OOH, display, etc.) | 10 days | Mon 4/15/24 | Fri 4/26/24
Share treatments with team for input | 2 days | Mon 4/29/24 | Tue 4/30/24
Revise treatments | 3 days | Wed 5/1/24 | Fri 5/3/24
Share with team for final round input | 2 days | Mon 5/6/24 | Tue 5/7/24
Finalize creative treatments | 3 days | Wed 5/8/24 | Fri 5/10/24
Video pre-production (location scouting, talent, etc.) | 10 days | Mon 5/13/24 | Fri 5/24/24
Video shoot | 5 days | Tue 5/28/24 | Mon 6/3/24
Video editing | 5 days | Tue 6/4/24 | Mon 6/10/24
Share :30 video rough cut with team for input | 1 day | Tue 6/11/24 | Tue 6/11/24
Revise rough cut | 2 days | Wed 6/12/24 | Thu 6/13/24
Share revised rough cut with team for input | 2 days | Fri 6/14/24 | Mon 6/17/24
Finalize rough cut | 2 days | Tue 6/18/24 | Wed 6/19/24
Produce :30 spot | 2 days | Thu 6/20/24 | Mon 6/24/24
Develop :15 cut-down and :12 social videos | 5 days | Tue 6/25/24 | Mon 7/1/24
Share :15 cut-down and :12 social videos with team for input | 3 days | Tue 7/2/24 | Fri 7/5/24
Finalize :15 and :12 videos | 3 days | Mon 7/8/24 | Wed 7/10/24
Final approval video assets | 1 day | Thu 7/11/24 | Thu 7/11/24
Develop OOH, display, and any other required assets | 10 days | Tue 6/25/24 | Tue 7/9/24
Share OOH, display, etc assets with team for input | 3 days | Wed 7/10/24 | Fri 7/12/24
Finalize OOH, display, etc assets | 5 days | Mon 7/15/24 | Fri 7/19/24
Build/package creative assets for trafficking | 5 days | Mon 7/22/24 | Fri 7/26/24
Tracking & Analysis | 77
Media tracking requirements provided | 5 days | Thu 4/11/24 | Wed 4/17/24
Tracking implementation on OSHE hosted website | 5 days | Thu 4/18/24 | Wed 4/24/24
Q/A to validate placement of tracking and data transfer | 5 days | Thu 4/25/24 | Wed 5/1/24
Dashboard requirements drafted | 5 days | Thu 4/11/24 | Wed 4/17/24
Dashboard requirements to team for input | 2 days | Thu 4/18/24 | Fri 4/19/24
Finalize Dashboard requirements | 2 days | Mon 4/22/24 | Tue 4/23/24
Dashboard requirements to vendor for implementation | 2 days | Wed 4/24/24 | Thu 4/25/24
Set-up of campaign dashboard | 10 days | Fri 4/26/24 | Thu 5/9/24
Validation of data in campaign dashboard | 5 days | Thu 5/2/24 | Wed 5/8/24
Dashboard goes live | 1 day | Thu 5/9/24 | Thu 5/9/24
Validate live campaign data going into dashboard | 1 day | Mon 1/22/24 | Mon 1/22/24
Media Execution | 79
Final negotiation with vendors | 10 days | Thu 4/11/24 | Wed 4/24/24
Issue insertion orders | 10 days | Thu 4/25/24 | Wed 5/8/24
Develop trafficking matrix | 10 days | Thu 5/9/24 | Wed 5/22/24
Traffic creative units | 5 days | Mon 7/29/24 | Fri 8/2/24
Launch | 6
Go live | 1
Daily updates provided to team | 5 days | Tue 8/6/24 | Mon 8/12/24
Optimization | 364
Daily monitoring of campaign performance | 10 days | Tue 8/6/24 | Mon 8/19/24
Weekly campaign optimization calls | 354 days | Tue 8/20/24 | Mon 1/5/26

## Expedited Milestones
COLLABORATING TEAM NAMES
MARKETING CAMPAIGN NAME
START DATE
Task Name | Number of Days | Start | Finish
Vendor Procurement | TBD
Draft Mini-Bid and Vendor Selection Scorecard | 3 days | Fri 1/19/24 | Tue 1/23/24
Review Mini Bid and Scorecard with internal stakeholders | 1 day | Wed 1/24/24 | Wed 1/24/24
Mini-Bid and Venddor Selection Scorecard Approval | 1 day | Thu 1/25/24 | Thu 1/25/24
Establish Vendor Selection Committee and Mini-Bid Administrator | 0 days | Thu 1/25/24 | Thu 1/25/24
Issue Mini-Bid solicitation | 1 day | Fri 1/26/24 | Fri 1/26/24
Question submission period | 3 days | Mon 1/29/24 | Wed 1/31/24
Question responses issued | 2 days | Thu 2/1/24 | Fri 2/2/24
Receive Vendor proposals | 5 days | Mon 2/5/24 | Fri 2/9/24
Schedule Vendor meetings | 2 days | Mon 2/12/24 | Tue 2/13/24
Vendor presentations | 3 days | Wed 2/14/24 | Fri 2/16/24
Score and select vendor based on Scorecard results | 1 day | Tue 2/20/24 | Tue 2/20/24
Vendor Notification | 1 day | Wed 2/21/24 | Wed 2/21/24
Issue PO | 5 days | Thu 2/22/24 | Wed 2/28/24
Debrief sessions with Vendors (if requested) | 5 days | Thu 2/29/24 | Wed 3/6/24
Onboarding/Discovery | TBD
Campaign kick-off meeting to review timing, discuss ways of working, how communication will work, etc. | 1 day | Wed 1/24/24 | Wed 1/24/24
Existing research, past campaign performance, etc. shared with OOI | 2 days | Thu 1/25/24 | Fri 1/26/24
Synthesize and analyze existing data | 5 days | Mon 1/29/24 | Fri 2/2/24
Share summary with team | 5 days | Mon 2/5/24 | Fri 2/9/24
Vendor Kick-Off meeting | 2 days | Thu 2/29/24 | Fri 3/1/24
Paid Search Launch | 22
Confirm website/pages paid search will drive traffic to | 0 days | Fri 3/1/24 | Fri 3/1/24
Develop paid search strategy, recommended budget, keywords and copy | 5 days | Mon 3/4/24 | Fri 3/8/24
Develop paid search tracking recommendation | 5 days | Mon 3/4/24 | Fri 3/8/24
Share paid search strategy, recommended budget, keywords and copy with team for input | 0 days | Fri 3/8/24 | Fri 3/8/24
Share paid search tracking recommendation with team for implementation | 3 days | Mon 3/11/24 | Wed 3/13/24
Team to provide strategy/budget/keyword/copy feedback | 3 days | Mon 3/11/24 | Wed 3/13/24
Implement and validate required campaign tracking | 5 days | Thu 3/14/24 | Wed 3/20/24
Revise paid search strategy, budget, keywords and copy | 3 days | Thu 3/14/24 | Mon 3/18/24
Finalize paid search strategy, budget, keywords and copy | 2 days | Tue 3/19/24 | Wed 3/20/24
Build out paid search campaign | 3 days | Thu 3/21/24 | Mon 3/25/24
Go live | 1 | 0 | 0
Begin weekly reporting | 5 days | Wed 3/27/24 | Wed 4/3/24
Paid Social Launch (assumes verified Facebook page exists) | 25
Develop Meta quick launch recommendation (budget and targeting strategy) | 10 days | Mon 3/25/24 | Mon 4/8/24
Share Meta quick launch recommendation + creative specs with team for input | 3 days | Tue 4/9/24 | Thu 4/11/24
Revise Meta quick launch recommendation | 3 days | Fri 4/12/24 | Tue 4/16/24
Finalize Meta quick launch recommendation | 2 days | Wed 4/17/24 | Thu 4/18/24
Develop static and dynamic creative assets | 5 days | Fri 4/5/24 | Thu 4/11/24
Share static and dynamic creative assets with team for input | 2 days | Fri 4/12/24 | Mon 4/15/24
Revise static and dynamic creative assets | 2 days | Tue 4/16/24 | Wed 4/17/24
Finalize static and dynamic creative assets | 1 day | Thu 4/18/24 | Thu 4/18/24
Build campaign | 1 day | Fri 4/19/24 | Fri 4/19/24
Go live | 1 | 0 | 0
Begin weekly reporting | 5 days | Tue 4/23/24 | Mon 4/29/24
Audience Research | 26
Share Audience Research Brief with team for input | 1 day | Wed 1/24/24 | Wed 1/24/24
Finalize Research Brief | 2 days | Thu 1/25/24 | Fri 1/26/24
Develop respondent recruiting copy + lead collection landing page | 0 days | Fri 1/26/24 | Fri 1/26/24
Provide recruiting copy to OSHE/HESAA for deployment | 0 days | Fri 1/26/24 | Fri 1/26/24
Recruit respondents | 10 days | Mon 1/29/24 | Fri 2/9/24
Screen/schedule respondents | 10 days | Tue 1/30/24 | Mon 2/12/24
Conduct ethnographic audience interviews | 10 days | Wed 1/31/24 | Tue 2/13/24
Synthesize and analyze findings | 10 days | Wed 2/14/24 | Wed 2/28/24
Present audience analysis, segments and personas | 1 day | Thu 2/29/24 | Thu 2/29/24
Strategy Development | 14
Develop Value Proposition and Creative Brief | 5 days | Fri 3/1/24 | Thu 3/7/24
Share Value Proposition and Creative Brief with team for input | 1 day | Fri 3/8/24 | Fri 3/8/24
Finalize Value Proposition and Creative Brief | 1 day | Mon 3/11/24 | Mon 3/11/24
Conduct competitive research | 7 days | Fri 3/1/24 | Mon 3/11/24
Develop Marketing Communication Strategy | 5 days | Tue 3/12/24 | Mon 3/18/24
Share Marketing Communication Strategy for input | 1 day | Tue 3/19/24 | Tue 3/19/24
Finalize Marketing Communicaiton Strategy | 1 day | Wed 3/20/24 | Wed 3/20/24
Creative Concepting | 10
Develop Creative Concepts (Scripts) | 5 days | Tue 3/12/24 | Mon 3/18/24
Share Creative Concepts with team for input | 2 days | Tue 3/19/24 | Wed 3/20/24
Finalize Creative concepts | 3 days | Thu 3/21/24 | Mon 3/25/24
Creative Validation | 24
Develop Concept Validation Brief | 2 days | Fri 3/8/24 | Mon 3/11/24
Share Brief with team for input | 2 days | Tue 3/12/24 | Wed 3/13/24
Finalize Brief | 1 day | Thu 3/14/24 | Thu 3/14/24
Develop Survey questions | 2 days | Fri 3/15/24 | Mon 3/18/24
Share Survey questions for input | 2 days | Tue 3/19/24 | Wed 3/20/24
Finalize Survey questions | 1 day | Thu 3/21/24 | Thu 3/21/24
Set-up Survey test in SurveyMonkey | 3 days | Fri 3/22/24 | Tue 3/26/24
QA Survey Set-up | 2 days | Wed 3/27/24 | Thu 3/28/24
Field test | 3 days | Mon 4/1/24 | Wed 4/3/24
Share out initial findings/identy winner | 1 day | Thu 4/4/24 | Thu 4/4/24
Develop analysis | 4 days | Fri 4/5/24 | Wed 4/10/24
Share analysis with team | 1 day | Thu 4/11/24 | Thu 4/11/24
Media Planning | 16
Develop Media Flowchart based on provided Marketing Communication Strategy | 5 days | Thu 3/21/24 | Wed 3/27/24
Share with team for input | 2 days | Thu 3/28/24 | Mon 4/1/24
Revise Media Flowchart | 3 days | Tue 4/2/24 | Thu 4/4/24
Share with team for input | 2 days | Fri 4/5/24 | Mon 4/8/24
Finalize Media Flowchart | 2 days | Tue 4/9/24 | Wed 4/10/24
Provide team with all required creative asset specifications | 1 day | Thu 4/11/24 | Thu 4/11/24
Update Creative Brief with required creative asset specifications | 1 day | Fri 4/12/24 | Fri 4/12/24
Creative Production | 72
Using winning concept, develop treatments for different formats (video, banner, OOH, display, etc.) | 10 days | Mon 4/15/24 | Fri 4/26/24
Share treatments with team for input | 2 days | Mon 4/29/24 | Tue 4/30/24
Revise treatments | 3 days | Wed 5/1/24 | Fri 5/3/24
Share with team for final round input | 2 days | Mon 5/6/24 | Tue 5/7/24
Finalize creative treatments | 3 days | Wed 5/8/24 | Fri 5/10/24
Video pre-production (location scouting, talent, etc.) | 10 days | Mon 5/13/24 | Fri 5/24/24
Video shoot | 5 days | Tue 5/28/24 | Mon 6/3/24
Video editing | 5 days | Tue 6/4/24 | Mon 6/10/24
Share :30 video rough cut with team for input | 1 day | Tue 6/11/24 | Tue 6/11/24
Revise rough cut | 2 days | Wed 6/12/24 | Thu 6/13/24
Share revised rough cut with team for input | 2 days | Fri 6/14/24 | Mon 6/17/24
Finalize rough cut | 2 days | Tue 6/18/24 | Wed 6/19/24
Produce :30 spot | 2 days | Thu 6/20/24 | Mon 6/24/24
Develop :15 cut-down and :12 social videos | 5 days | Tue 6/25/24 | Mon 7/1/24
Share :15 cut-down and :12 social videos with team for input | 3 days | Tue 7/2/24 | Fri 7/5/24
Finalize :15 and :12 videos | 3 days | Mon 7/8/24 | Wed 7/10/24
Final approval video assets | 1 day | Thu 7/11/24 | Thu 7/11/24
Develop OOH, display, and any other required assets | 10 days | Tue 6/25/24 | Tue 7/9/24
Share OOH, display, etc assets with team for input | 3 days | Wed 7/10/24 | Fri 7/12/24
Finalize OOH, display, etc assets | 5 days | Mon 7/15/24 | Fri 7/19/24
Build/package creative assets for trafficking | 5 days | Mon 7/22/24 | Fri 7/26/24
Tracking & Analysis | 77
Media tracking requirements provided | 5 days | Thu 4/11/24 | Wed 4/17/24
Tracking implementation on OSHE hosted website | 5 days | Thu 4/18/24 | Wed 4/24/24
Q/A to validate placement of tracking and data transfer | 5 days | Thu 4/25/24 | Wed 5/1/24
Dashboard requirements drafted | 5 days | Thu 4/11/24 | Wed 4/17/24
Dashboard requirements to team for input | 2 days | Thu 4/18/24 | Fri 4/19/24
Finalize Dashboard requirements | 2 days | Mon 4/22/24 | Tue 4/23/24
Dashboard requirements to vendor for implementation | 2 days | Wed 4/24/24 | Thu 4/25/24
Set-up of campaign dashboard | 10 days | Fri 4/26/24 | Thu 5/9/24
Validation of data in campaign dashboard | 5 days | Thu 5/2/24 | Wed 5/8/24
Dashboard goes live | 1 day | Thu 5/9/24 | Thu 5/9/24
Validate live campaign data going into dashboard | 1 day | Mon 1/22/24 | Mon 1/22/24
Media Execution | 79
Final negotiation with vendors | 10 days | Thu 4/11/24 | Wed 4/24/24
Issue insertion orders | 10 days | Thu 4/25/24 | Wed 5/8/24
Develop trafficking matrix | 10 days | Thu 5/9/24 | Wed 5/22/24
Traffic creative units | 5 days | Mon 7/29/24 | Fri 8/2/24
Launch | 6
Go live | 1
Daily updates provided to team | 5 days | Tue 8/6/24 | Mon 8/12/24
Optimization | 364
Daily monitoring of campaign performance | 10 days | Tue 8/6/24 | Mon 8/19/24
Weekly campaign optimization calls | 354 days | Tue 8/20/24 | Mon 1/5/26